## CP Tracker Dashboard
Project_Number | CP | Conv Length | Elec Device Count | Mech Install | Elect Install | Path to Run-In | Mech Finishing | As of 6/17/26
B-24-04663 | Total | 641306 | 4951 | 2.768% | 2.955% | 0.4065% | 0%
B-24-04663 | CP01 | 28436 | 296 | 0% | 2% | 0% | 0%
B-24-04663 | CP02 | 41164 | 273 | 0% | 2% | 0% | 0%
B-24-04663 | CP03 | 37242 | 500 | 0% | 0% | 0% | 0%
B-24-04663 | CP09 | 81148 | 150 | 0% | 6% | 0% | 0%
B-24-04663 | CP11 | 22899 | 175 | 0% | 2% | 0% | 0%
B-24-04663 | CP40 | 40657 | 496 | 24.23% | 6.181% | 0% | 0%
B-24-04663 | CP41 | 19594 | 425 | 0% | 9.188% | 0% | 0%
B-24-04663 | CP42 | 14789 | 222 | 29.52% | 12.66% | 17.63% | 0%
B-24-04663 | CP50 | 48427 | 500 | 7.308% | 6.2% | 0% | 0%
B-24-04663 | CP51 | 73424 | 500 | 0% | 0% | 0% | 0%
B-24-04663 | CP52 | 148635 | 500 | 0% | 0% | 0% | 0%
B-24-04663 | CP80 | 34877 | 488 | 0% | 2% | 0% | 0%
B-24-04663 | CP81 | 25167 | 158 | 0% | 6% | 0% | 0%
B-24-04663 | CP91 | 24847 | 268 | 0% | 2% | 0% | 0%
Total |  | 641306 | 4951 | 2.768% | 3.6% | 0.4065% | 0%

## CP40 (2) (hidden)
CP | Asset | Length | Task Name | Start | Finish | Status | % Complete
CP40 | 40255 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Complete | 100%
CP40 | 40355 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Complete | 100%
CP40 | 40230 | 198 | Staging & Prep | 2026-05-04 | 2026-05-15 | Complete | 100%
CP40 | 40330 | 198 | Staging & Prep | 2026-05-04 | 2026-05-15 | Complete | 100%
CP40 | 40405 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Complete | 100%
CP40 | 40605 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40005 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40010 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40015 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40020 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40025 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40030 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40105 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40110 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40115 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40120 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40125 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40130 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40205 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40210 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40215 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40220 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40225 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40235 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40245 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40248 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40250 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40305 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40310 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40312 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40314 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40316 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40318 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40320 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40325 | ` | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40335 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40345 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40348 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40350 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40410 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40415 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40420 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40425 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40430 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40610 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40615 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40620 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40625 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40630 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40703 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40704 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40705 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40706 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40707 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40708 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40709 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40710 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40711 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40712 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40713 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40714 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40715 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40716 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40717 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40718 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40719 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40720 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40721 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40722 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40723 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40724 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40725 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40726 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40727 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40728 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40729 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40730 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40731 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40732 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40733 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40734 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40735 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40736 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40737 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40738 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40739 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40740 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40741 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40742 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40743 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40744 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40745 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40746 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40747 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40748 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40749 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40750 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40751 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40752 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40753 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40754 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40755 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40756 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40757 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40758 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40759 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40760 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40761 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40762 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40763 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40764 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40765 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40766 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40767 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40769 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40770 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40771 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40772 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40905 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40910 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40915 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40920 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40925 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40930 | 1 | Staging & Prep | 2026-05-04 | 2026-05-15 | Not Started | 0%
CP40 | 40255 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Complete | 100%
CP40 | 40355 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Complete | 100%
CP40 | 40230 | 198 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Complete | 100%
CP40 | 40330 | 198 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Complete | 100%
CP40 | 40405 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Complete | 100%
CP40 | 40605 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40005 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40010 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40015 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40020 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40025 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40030 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40105 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40110 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40115 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40120 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40125 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40130 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40205 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40210 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40215 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40220 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40225 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40235 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40245 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40248 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40250 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40305 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40310 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40312 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40314 | 1 | Anchored & Leveled | 2026-05-18 | 2026-05-27 | Not Started | 0%
CP40 | 40316 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40318 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40320 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40325 | ` | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40335 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40345 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40348 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40350 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40410 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40415 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40420 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40425 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40430 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40610 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40615 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40620 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40625 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40630 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40703 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40704 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40705 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40706 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40707 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40708 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40709 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40710 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40711 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40712 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40713 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40714 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40715 | 1 | Anchored & Leveled | 2026-05-28 | 2026-06-10 | Not Started | 0%
CP40 | 40716 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40717 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40718 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40719 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40720 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40721 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40722 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40723 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40724 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40725 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40726 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40727 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40728 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40729 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40730 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40731 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40732 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40733 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40734 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40735 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40736 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40737 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40738 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40739 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40740 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40741 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40742 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40743 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40744 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40745 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40746 | 1 | Anchored & Leveled | 2026-06-11 | 2026-06-24 | Not Started | 0%
CP40 | 40747 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40748 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40749 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40750 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40751 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40752 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40753 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40754 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40755 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40756 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40757 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40758 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40759 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40760 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40761 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40762 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40763 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40764 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40765 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40766 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40767 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40769 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40770 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40771 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40772 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40905 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40910 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40915 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40920 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40925 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40930 | 1 | Anchored & Leveled | 2026-06-25 | 2026-07-08 | Not Started | 0%
CP40 | 40255 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40355 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40230 | 198 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40330 | 198 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40405 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40605 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40005 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40010 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40015 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40020 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40025 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40030 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40105 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40110 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40115 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40120 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40125 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40130 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40205 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40210 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40215 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40220 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40225 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40235 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40245 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40248 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40250 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40305 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40310 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40312 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40314 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40316 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40318 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40320 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40325 | ` | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40335 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40345 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40348 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40350 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40410 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40415 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40420 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40425 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40430 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40610 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40615 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40620 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40625 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40630 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40703 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40704 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40705 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40706 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40707 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40708 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40709 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40710 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40711 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40712 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40713 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40714 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40715 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40716 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40717 | 1 | Belting | 2026-06-25 | 2026-07-04 | Not Started | 0%
CP40 | 40718 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40719 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40720 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40721 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40722 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40723 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40724 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40725 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40726 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40727 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40728 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40729 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40730 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40731 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40732 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40733 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40734 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40735 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40736 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40737 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40738 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40739 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40740 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40741 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40742 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40743 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40744 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40745 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40746 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40747 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40748 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40749 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40750 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40751 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40752 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40753 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40754 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40755 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40756 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40757 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40758 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40759 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40760 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40761 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40762 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40763 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40764 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40765 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40766 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40767 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40769 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40770 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40771 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40772 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40905 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40910 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40915 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40920 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40925 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40930 | 1 | Belting | 2026-07-06 | 2026-07-15 | Not Started | 0%
CP40 | 40255 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40355 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40230 | 198 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40330 | 198 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40405 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40605 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40005 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40010 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40015 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40020 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40025 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40030 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40105 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40110 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40115 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40120 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40125 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40130 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40205 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40210 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40215 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40220 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40225 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40235 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40245 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40248 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40250 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40305 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40310 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40312 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40314 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40316 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40318 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40320 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40325 | ` | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40335 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40345 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40348 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40350 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40410 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40415 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40420 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40425 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40430 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40610 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40615 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40620 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40625 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40630 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40703 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40704 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40705 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40706 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40707 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40708 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40709 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40710 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40711 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40712 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40713 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40714 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40715 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40716 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40717 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40718 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40719 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40720 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40721 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40722 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40723 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40724 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40725 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40726 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40727 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40728 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40729 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40730 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40731 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40732 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40733 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40734 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40735 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40736 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40737 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40738 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40739 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40740 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40741 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40742 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40743 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40744 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40745 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40746 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40747 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40748 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40749 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40750 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40751 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40752 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40753 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40754 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40755 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40756 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40757 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40758 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40759 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40760 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40761 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40762 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40763 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40764 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40765 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40766 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40767 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40769 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40770 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40771 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40772 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40905 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40910 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40915 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40920 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40925 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40930 | 1 | Bottom Pans | 2026-07-15 | 2026-07-19 | Not Started | 0%
CP40 | 40255 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40355 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40230 | 198 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 100%
CP40 | 40330 | 198 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 100%
CP40 | 40405 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 100%
CP40 | 40605 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 100%
CP40 | 40005 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40010 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40015 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40020 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40025 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40030 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40105 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40110 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40115 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40120 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40125 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40130 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40205 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40210 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40215 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40220 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40225 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40235 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40245 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40248 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40250 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40305 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40310 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40312 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40314 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40316 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40318 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40320 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40325 | ` | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40335 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40345 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40348 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40350 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40410 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40415 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40420 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40425 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40430 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40610 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40615 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40620 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40625 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40630 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40703 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40704 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40705 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40706 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40707 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40708 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40709 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40710 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40711 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40712 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40713 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40714 | 1 | Side Guide | 2026-07-20 | 2026-07-29 | Not Started | 0%
CP40 | 40715 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40716 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40717 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40718 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40719 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40720 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40721 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40722 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40723 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40724 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40725 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40726 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40727 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40728 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40729 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40730 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40731 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40732 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40733 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40734 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40735 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40736 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40737 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40738 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40739 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40740 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40741 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40742 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40743 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40744 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40745 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40746 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40747 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40748 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40749 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40750 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40751 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40752 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40753 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40754 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40755 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40756 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40757 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40758 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40759 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40760 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40761 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40762 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40763 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40764 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40765 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40766 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40767 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40769 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40770 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40771 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40772 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40905 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40910 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40915 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40920 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40925 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40930 | 1 | Side Guide | 2026-07-30 | 2026-08-08 | Not Started | 0%
CP40 | 40255 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40355 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40230 | 198 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40330 | 198 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40405 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40605 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40005 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40010 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40015 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40020 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40025 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40030 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40105 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40110 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40115 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40120 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40125 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40130 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40205 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40210 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40215 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40220 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40225 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40235 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40245 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40248 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40250 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40305 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40310 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40312 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40314 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40316 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40318 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40320 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40325 | ` | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40335 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40345 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40348 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40350 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40410 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40415 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40420 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40425 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40430 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40610 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40615 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40620 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40625 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40630 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40703 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40704 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40705 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40706 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40707 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40708 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40709 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40710 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40711 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40712 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40713 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40714 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40715 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40716 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40717 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40718 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40719 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40720 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40721 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40722 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40723 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40724 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40725 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40726 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40727 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40728 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40729 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40730 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40731 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40732 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40733 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40734 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40735 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40736 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40737 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40738 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40739 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40740 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40741 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40742 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40743 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40744 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40745 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40746 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40747 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40748 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40749 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40750 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40751 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40752 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40753 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40754 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40755 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40756 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40757 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40758 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40759 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40760 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40761 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40762 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40763 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40764 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40765 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40766 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40767 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40769 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40770 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40771 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40772 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40905 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40910 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40915 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40920 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40925 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40930 | 1 | Netting | 2026-08-09 | 2026-08-16 | Blocked | 0%
CP40 | 40255 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40355 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40230 | 198 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40330 | 198 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40405 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40605 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40005 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40010 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40015 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40020 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40025 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40030 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40105 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40110 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40115 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40120 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40125 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40130 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40205 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40210 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40215 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40220 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40225 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40235 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40245 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40248 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40250 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40305 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40310 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40312 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40314 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40316 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40318 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40320 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40325 | ` | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40335 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40345 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40348 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40350 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40410 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40415 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40420 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40425 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40430 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40610 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40615 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40620 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40625 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40630 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40703 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40704 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40705 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40706 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40707 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40708 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40709 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40710 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40711 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40712 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40713 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40714 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40715 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40716 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40717 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40718 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40719 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40720 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40721 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40722 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40723 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40724 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40725 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40726 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40727 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40728 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40729 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40730 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40731 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40732 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40733 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40734 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40735 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40736 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40737 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40738 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40739 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40740 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40741 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40742 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40743 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40744 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40745 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40746 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40747 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40748 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40749 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40750 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40751 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40752 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40753 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40754 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40755 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40756 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40757 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40758 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40759 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40760 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40761 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40762 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40763 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40764 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40765 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40766 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40767 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40769 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40770 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40771 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40772 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40905 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40910 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40915 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40920 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40925 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40930 | 1 | Run-in | 2026-11-11 | 2026-11-17 | Not Started | 0%

## CP40 (2) Pivot (hidden)
Count of Status | Column Labels
Row Labels | Blocked | Complete | Not Started | Grand Total
Anchored & Leveled |  | 5 | 119 | 124
Belting |  |  | 124 | 124
Bottom Pans |  |  | 124 | 124
Netting | 124 |  |  | 124
Run-in |  |  | 124 | 124
Side Guide |  |  | 124 | 124
Staging & Prep |  | 5 | 119 | 124
Grand Total | 124 | 10 | 734 | 868

## AP Tracker Mechanical Dashboard
Overall Totals (As of 6/30/26) - CP52 Not Included
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 59.8 | 23.095 | 38.62%
Erected | 30% | 179.4 | 41.07 | 22.89%
Anchored | 10% | 59.8 | 10.17 | 17.01%
Belting | 20% | 119.6 | 20.14 | 16.84%
Bottom Pans | 5% | 29.9 | 3.67 | 12.27%
Side Guide | 20% | 119.6 | 17.6625 | 14.77%
Netting | 5% | 29.9 | 6.7 | 22.41%
Total Completion | 100% | 598 | 122.5075 | 20.49%

## CP40
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide - 20% |  |  |  |  | Netting - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
CP40 | 40255 | 1 | 2026-05-04 | 2026-05-15 | Complete | Not installed by missing straddle supports | 100% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 100% | 2026-06-25 | 2026-07-04 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40355 | 1 | 2026-05-04 | 2026-05-15 | Complete | Not installed by missing straddle supports | 100% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 100% | 2026-06-25 | 2026-07-04 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40230 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Complete | Need to replace short supports with correct height | 90% | 2026-05-18 | 2026-05-27 | Complete | Need to replace short supports with correct height | 100% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm on Belt joining m/c | 0% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40330 | 1 | 2026-05-04 | 2026-05-15 | Complete | Missing drive | 100% | 2026-05-18 | 2026-05-27 | Complete | Need to replace short supports with correct height | 90% | 2026-05-18 | 2026-05-27 | Complete | Need to replace short supports with correct height | 100% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm on Belt joining m/c | 0% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40405 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40605 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40005 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40010 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40015 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40020 | 1 | 2026-05-04 | 2026-05-15 | Complete | 40036700-11209549 | 90% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40025 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 60% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40030 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40105 | 1 | 2026-05-04 | 2026-05-15 | Complete | 47039800-9636785 | 90% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40110 | 1 | 2026-05-04 | 2026-05-15 | Complete | 47007400-11209515 | 90% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40115 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40120 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40125 | 1 | 2026-05-04 | 2026-05-15 | Complete | 49253330-11554036 | 90% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40130 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 50% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40205 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40210 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40215 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40220 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40225 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40235 | 1 | 2026-05-04 | 2026-05-15 | Complete | Not installed by missing straddle supports | 60% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40245 | 1 | 2026-05-04 | 2026-05-15 | Not Started | PBC NO INFO ISC | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40248 | 1 | 2026-05-04 | 2026-05-15 | Complete | 47012000-11417507 | 90% | 2026-05-18 | 2026-05-27 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-18 | 2026-05-27 | Not Started | Upstream & Downstream conveyor not installed | 50% | 2026-06-25 | 2026-07-04 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-15 | 2026-07-19 | Not Started | Waiting for installation | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40250 | 1 | 2026-05-04 | 2026-05-15 | Complete | wrong hand | 90% | 2026-05-18 | 2026-05-27 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-18 | 2026-05-27 | Not Started | Upstream & Downstream conveyor not installed | 90% | 2026-06-25 | 2026-07-04 | Complete | Upstream & Downstream conveyor not installed | 100% | 2026-07-15 | 2026-07-19 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40305 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40310 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40312 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40314 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-18 | 2026-05-27 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40316 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40318 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 100% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40320 | 1 | 2026-05-04 | 2026-05-15 | Complete | 47007400-11209531 | 90% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40325 | 1 | 2026-05-04 | 2026-05-15 | Complete |  | 80% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-05-28 | 2026-06-10 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-06-25 | 2026-07-04 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-15 | 2026-07-19 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-07-20 | 2026-07-29 | Not Started | Area Beyond Grid 8 ,not available for Install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Area Beyond Grid 8 ,not available for Install | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40335 | 1 | 2026-05-04 | 2026-05-15 | Complete | Not installed by missing straddle supports | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material Delivery (Straddle Support) | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40345 | 1 | 2026-05-04 | 2026-05-15 | Not Started | PBC NO INFO ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery (Transnorm Curve) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40348 | 1 | 2026-05-04 | 2026-05-15 | Complete | 47006700-10347691 | 80% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 20% | 2026-06-25 | 2026-07-04 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-15 | 2026-07-19 | Not Started | Waiting for installation | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
47012000-11417507
CP40 | 40350 | 1 | 2026-05-04 | 2026-05-15 | Complete | wrong hand | 90% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed |  | 2026-06-25 | 2026-07-04 | Complete | Upstream & Downstream conveyor not installed | 100% | 2026-07-15 | 2026-07-19 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40410 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 50% | 2026-05-28 | 2026-06-10 | Not Started | Expected Design Change | 0% | 2026-05-28 | 2026-06-10 | Not Started | Expected Design Change | 30% | 2026-06-25 | 2026-07-04 | Not Started | Expected Design Change | 0% | 2026-07-15 | 2026-07-19 | Not Started | Expected Design Change | 0% | 2026-07-20 | 2026-07-29 | Not Started | Expected Design Change | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40415 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Powedercoated HD supports) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Powedercoated HD supports) | 20% | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started |  | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40420 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Powedercoated HD supports) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Powedercoated HD supports) | 0% | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started | NA | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40425 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 100% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40430 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 50% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-06-25 | 2026-07-04 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-15 | 2026-07-19 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | Upstream & Downstream conveyor not installed | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40610 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 50% | 2026-05-28 | 2026-06-10 | Not Started | Expected Design Change | 0% | 2026-05-28 | 2026-06-10 | Not Started | Expected Design Change | 0% | 2026-06-25 | 2026-07-04 | Not Started | Expected Design Change | 0% | 2026-07-15 | 2026-07-19 | Not Started | Expected Design Change | 0% | 2026-07-20 | 2026-07-29 | Not Started | Expected Design Change | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40615 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 50% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Powedercoated HD supports) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material Delivery (Powedercoated HD supports) | 0% | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
49383930-11548787
49253430-11211669
CP40 | 40620 | 1 | 2026-05-04 | 2026-05-15 | In Progress | It won't be installed with the current plans | 25% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Powedercoated HD supports) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing material delivery (Powedercoated HD supports) | 0% | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started | NA | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40625 | 1 | 2026-05-04 | 2026-05-15 | Not Started | It won't be installed with the current plans | 0% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm |  | 2026-06-25 | 2026-07-04 | Not Started | NA | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40630 | 1 | 2026-05-04 | 2026-05-15 | Not Started | It won't be installed with the current plans | 0% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-05-28 | 2026-06-10 | Not Started | Upstream & Downstream conveyor not installed |  | 2026-06-25 | 2026-07-04 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-15 | 2026-07-19 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-07-20 | 2026-07-29 | Not Started | Upstream & Downstream conveyor not installed | 0% | 2026-08-09 | 2026-08-16 | Blocked | Upstream & Downstream conveyor not installed | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40701 | 1 | 2026-05-04 | 2026-05-15 | Not Started |  | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40702 | 1 | 2026-05-04 | 2026-05-15 | Not Started |  | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40703 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40704 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40705 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40706 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40707 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40708 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40709 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40710 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40711 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40712 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40713 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40714 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40715 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40716 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40717 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40718 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40719 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40720 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40721 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40722 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40723 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40724 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40725 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40726 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40727 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40728 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40729 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40730 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40731 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40732 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40733 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40734 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40735 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40736 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40737 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40738 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40739 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40740 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40741 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40742 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40743 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40744 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40745 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40746 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40747 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40748 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40749 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40750 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40751 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40752 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40753 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40754 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40755 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40756 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40757 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40758 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40759 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40760 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40761 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40762 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40763 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40764 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40765 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40766 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40767 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40769 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40770 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40771 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40772 | 1 | 2026-05-04 | 2026-05-15 | Not Started | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (SOPER'd MDR) |  | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery (SOPER'd MDR) | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40905 | 1 | 2026-05-04 | 2026-05-15 | Not Started | 40099300-11212065 | 50% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm | 100% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm |  | 2026-07-06 | 2026-07-15 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-30 | 2026-08-08 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Blocked | 3-Phase to confirm | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
[6 empty] | 40036200-11212067 | [10 empty] | 0%
CP40 | 40910 | 1 | 2026-05-04 | 2026-05-15 | In progress | 47140800-11212107 | 50% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm |  | 2026-07-06 | 2026-07-15 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-30 | 2026-08-08 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Blocked | 3-Phase to confirm | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40915 | 1 | 2026-05-04 | 2026-05-15 | In progress | 49253530-11212053 | 50% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-08 | Not Started | 3-Phase to confirm | 0% | 2026-07-06 | 2026-07-15 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-30 | 2026-08-08 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
[6 empty] | 49253330-11212051 | [10 empty] | 0%
CP40 | 40920 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Not Started | Upstrem & downstrem conveyors are not installed | 0% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40925 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Not Started | Upstrem & downstrem conveyors are not installed | 0% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Blocked | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
CP40 | 40930 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Not Started | Complete | 100% | 2026-06-25 | 2026-07-08 | Not Started |  | 0% | 2026-07-06 | 2026-07-15 | Not Started | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing material delivery (Transnorm Curve) | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
Total |  | 126 |  |  |  |  | 33.93% |  |  |  |  | 6.19% |  |  |  |  | 0% |  |  |  |  | 5.556% |  |  |  |  | 5.556% |  |  |  |  | 4.762% |  |  |  |  | 4.762% |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 12.6 | 4.275 | 33.93%
Erected | 30% | 37.8 | 2.34 | 6.19%
Anchored | 10% | 12.6 | 0.86 | 6.825%
Belting | 20% | 25.2 | 1.4 | 5.556%
Bottom Pans | 5% | 6.3 | 0.35 | 5.556%
Side Guide | 20% | 25.2 | 1.2 | 4.762%
Netting | 5% | 6.3 | 0.3 | 4.762%
Total Completion | 100% | 126 | 10.725 | 8.512%
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IS ASSY.12-0.34"BF.RH.ADVANCED.2"CTRS.3 FT ZN OUTSIDE OPP SIDE.G196PR.RIVER GRAY
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB SKEW INT ASSY 2"C.RIGHT SKEW.72.34"BF.G196PR.RIVER GRAY
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END DRV ASSY UH.34BF.LH BELT.LH PU.STD DRV SHV.G196PR.BAL-2HP-460V-PREM.DGE-202-A-05-R-140.DVR-P30-8M-30-1210.DVN-P56-8M-30-2012.GB-HT200-1064-8M-30.430"LG BELT.RIVER GRAY
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART DEC LWR TRNS.34"BF.30"ZN, 3ZN.LH WIRE.RLR LOW.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT.PREM DEC BELT DGR HON HTSS BRK.RIVER GRAY Reply: Missing materials
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END DRV ASSY SM.40BF.RH BELT.LH PU.STD DRV SHV.G196AB.BAL-1HP-460V-PREM.DGE-202-A-15-L-140.DVR-P32-8M-30-1210.DVN-P40-8M-30-2012.GB-HT200-720-8M-30.270"LG BELT.RIVER GRAY Reply: Drive is not on site
Note on G29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: · Crossover (wrong hand) · End idler (wrong hand) · Drive wrong hand (wrong hand)
Note on G36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END DRV ASSY UH.34BF.RH BELT.LH PU.STD DRV SHV.G196AB.BAL-1HP-460V-PREM.DGE-202-A-10-R-140.DVR-P32-8M-30-1210.DVN-P44-8M-30-2012.GB-HT200-1040-8M-30.405"LG BELT.RIVER GRAY
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END IDL ASSY.40"BF.RH BELT.G196AB.RIVER GRAY
Note on G41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END DRV ASSY SM.40BF.RH BELT.LH PU.STD DRV SHV.G196AB.BAL-1HP-460V-PREM.DGE-202-A-15-L-140.DVR-P32-8M-30-1210.DVN-P40-8M-30-2012.GB-HT200-720-8M-30.270"LG BELT.RIVER GRAY Reply: Drive is not on site
Note on G42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: · Crossover (wrong hand) · End idler (wrong hand) · Drive wrong hand (wrong hand)
Note on G43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It won't be installed with the current plans while waiting for the new design by M.E
Note on G57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710 JCT 30D LM.34"BF.3"CTRS.U83A CVR JCT HON STSS.RLR LOW.50LB WHL.180FPM INT.HON2018.RMT CNTL.BNR X2X.WH-490027.RIVER GRAY
Note on G58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on G126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IQ DIRECT CTR DRV ASSY.40"BF.9-0.LH.DIRECT DRIVE.AIR TRANS.2"CTRS.G196AB-BK.BAL-3HP-460V-PREM.DGE-30-A-15-H-180.DODGE A30.RIVER GRAY
Note on G127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IS ASSY.12-0.40"BF.LH.AIR TRANS.2"CTRS.G196AB-BK.RIVER GRAY
Note on G128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB SKEW INF ED ASSY UH.40"BF.LH BELT.RH PU.STD DRV SHV.G196AB.RH SKEW.BAL-2HP-460V-PREM.DGE-202-A-10-L-140.DVR-P40-8M-30-2012.DVN-P48-8M-30-2012.GB-HT200-1064-8M-30.605"LG BELT.RIVER GRAY
Note on G129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART DEC UPR TRNS.34"BF.30"ZN, 3ZN.RH WIRE.RLR LOW.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496655.PREM HORZ BELT DGR HON HTSS.PREM DEC BELT DGR HON HTSS BRK.RIVER GRAY
Note on G130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART DEC LWR TRNS.34"BF.30"ZN, 3ZN.RH WIRE.RLR LOW.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT.PREM DEC BELT DGR HON HTSS BRK.RIVER GRAY

## CP41
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Note | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP41 | 41035 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 95% | 2026-05-18 | 2026-05-27 | Complete | Complete | 95% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | In Progress | Missing Material Delivery (IQ bed) | 50% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | In Progress | Missing Material Delivery (IQ bed) | 80% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41055 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Need adjustment with scanner | 100% | 2026-05-18 | 2026-05-27 | Complete | Need adjustment with scanner | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Not Started | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41080 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Not started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Not Started | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41395 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41445 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41545 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | In Progress | Connected Transnoem not installed | 70% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41645 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | In Progress | 3-Phase to confirm | 10% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41745 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41845 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Connected Transnorm (PBC) not on site | 0% | 2026-05-18 | 2026-05-27 | Complete | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Complete | 3-Phase to confirm | 50% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41032 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 20% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 20% | 2026-06-25 | 2026-07-04 | Not Started | Need update from 3-phase | 0% | 2026-07-15 | 2026-07-19 | Not Started | Need update from 3-phase | 0% | 2026-07-20 | 2026-07-29 | Not Started | Need update from 3-phase | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41040 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (VB) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery (VB) | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41045 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Complete | 100% | 2026-06-25 | 2026-07-04 | Not Started | Complete | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41065 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | In Progress | Need adjustment with scanner | 50% | 2026-05-18 | 2026-05-27 | In Progress | Need adjustment with scanner | 50% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | In Progress | 3-Phase to confirm | 50% | 2026-08-09 | 2026-08-16 | Not Started | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41085 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Not Started | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41115 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41120 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41125 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41130 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41535 | 1 | 2026-05-04 | 2026-05-15 | Not Started | CRV (PBC) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41435 | 1 | 2026-05-04 | 2026-05-15 | In progress | In progress | 20% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41325 | 1 | 2026-05-04 | 2026-05-15 | In progress | In progress | 20% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41330 | 1 | 2026-05-04 | 2026-05-15 | Complete | 5’ 6” is not on site | 95% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41335 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Not Started | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41340 | 1 | 2026-05-04 | 2026-05-15 | Complete | CRV (PBC) | 90% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41345 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-18 | 2026-05-27 | Not Started | Wrong colour drive (VB) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Wrong colour drive (VB) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Wrong colour drive (VB) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Wrong colour drive (VB) | 0% | 2026-07-20 | 2026-07-29 | Not Started | Wrong colour drive (VB) | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41375 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41380 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41385 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-05-18 | 2026-05-27 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Complete | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41390 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41425 | 1 | 2026-05-04 | 2026-05-15 | Complete | is not on site | 100% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-18 | 2026-05-27 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41430 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-18 | 2026-05-27 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41440 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-05-18 | 2026-05-27 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Connected Transnorm (PBC) not on site | 70% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41525 | 1 | 2026-05-04 | 2026-05-15 | Complete | Is not on site | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41530 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41535 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41540 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41625 | 1 | 2026-05-04 | 2026-05-15 | Complete | 01 .03 is not on site | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41630 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41635 | 1 | 2026-05-04 | 2026-05-15 | Complete | CURVES (PBC) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41640 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | In Progress | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41725 | 1 | 2026-05-04 | 2026-05-15 | Complete | .01 .03 is not on site | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41730 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | In Progress | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41735 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41740 | 1 | 2026-05-04 | 2026-05-15 | Not Started | Not Started | 100% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Not Started | Connected Transnoem not installed | 70% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41825 | 1 | 2026-05-04 | 2026-05-15 | Complete | Curve is not on site | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 50% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Not Started | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41830 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41835 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41840 | 1 | 2026-05-04 | 2026-05-15 | Complete | 9’ 0” is not on site | 100% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-05-28 | 2026-06-10 | Not Started | 3-Phase to confirm | 0% | 2026-06-25 | 2026-07-04 | Not Started | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41875 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-06-25 | 2026-07-04 | Complete | MDR Belted Section | 100% | 2026-07-15 | 2026-07-19 | Not Started | Missing Upstrem / Downstrem Conveyor installation | 0% | 2026-07-20 | 2026-07-29 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41880 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-05-28 | 2026-06-10 | Not Started | Connected Transnorm (PBC) not on site | 0% | 2026-06-25 | 2026-07-04 | Complete | 3-Phase to confirm | 0% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-20 | 2026-07-29 | Not Started | 3-Phase to confirm | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41885 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (Transnorm) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41890 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | In Progress | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41895 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-05-28 | 2026-06-10 | Complete | Complete | 100% | 2026-06-25 | 2026-07-04 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41901 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41902 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41903 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41904 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41905 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41906 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41907 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41908 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41909 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41910 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-05-28 | 2026-06-10 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41911 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41912 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-04 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41913 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41914 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41915 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41916 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41917 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41918 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41919 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41920 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41921 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41922 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41923 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41924 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41925 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41926 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41927 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41928 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41929 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41930 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41931 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41932 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41933 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41934 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41935 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41936 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41937 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41938 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41939 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41940 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41941 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-11 | 2026-06-24 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41942 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41943 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41944 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41945 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41946 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41947 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41948 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41949 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41950 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41951 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41952 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41953 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41954 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41955 | 1 | 2026-05-04 | 2026-05-15 | No Info ISC | No Info ISC | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41956 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-06-25 | 2026-07-08 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-06 | 2026-07-15 | Not Started | Missing Material Delivery (MDR + Chute) | 0% | 2026-07-15 | 2026-07-19 | Not Started | Missing Material Delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Missing Material Delivery | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41050 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | In Progress | Need adjustment with scanner | 100% | 2026-06-25 | 2026-07-08 | In Progress | Need adjustment with scanner | 80% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Not Started | 3-Phase to confirm | 0% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Not Started | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41320 | 1 | 2026-05-04 | 2026-05-15 | Complete | Is not on site | 95% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Missing material delivery | 0% | 2026-07-06 | 2026-07-15 | Complete | NA- MDR | 100% | 2026-07-15 | 2026-07-19 | Not Started | 3-phase to confirm | 0% | 2026-07-30 | 2026-08-08 | Complete | NA-prefitted SG | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41370 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41420 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41520 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41620 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41720 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41820 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP41 | 41870 | 1 | 2026-05-04 | 2026-05-15 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-06-25 | 2026-07-08 | Complete | Complete | 100% | 2026-07-06 | 2026-07-15 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
Total |  | 118 |  |  |  |  | 35.72% |  |  |  |  | 22.16% |  |  |  |  | 19.92% |  |  |  |  | 33.47% |  |  |  |  | 22.03% |  |  |  |  | 32.2% |  |  |  |  | 95.76% |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 11.8 | 4.215 | 35.72%
Erected | 30% | 35.4 | 7.845 | 22.16%
Anchored | 10% | 11.8 | 2.35 | 19.92%
Belting | 20% | 23.6 | 7.9 | 33.47%
Bottom Pans | 5% | 5.9 | 1.3 | 22.03%
Side Guide | 20% | 23.6 | 7.6 | 32.2%
Netting | 5% | 5.9 | 5.65 | 95.76%
Total Completion | 100% | 118 | 36.86 | 31.24%
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It couldn't be completed due to IQZF 3'0 extra length on the unit. This was caused because the Drive came with a wrong length intermediate (12'0 instead of 9'0). Parts numbers match with ISC.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CURVES (PBC)
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .01 .02 .03
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on G53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBC
Note on F55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station Reply: Work Station
Note on F61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station
Note on F110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Station

## CP42
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP42 | 42255 | 1 | 2026-05-04 | 2026-05-13 | Complete | end idler missing | 100% | 2026-05-14 | 2026-05-23 | Not Started | Will be a new design (short supports) | 0% | 2026-05-14 | 2026-05-23 | Not Started | Not anchored due to concrete joint and future change on the structure MPH13 | 0% | 2026-06-25 | 2026-07-09 | WIP | missing material delivery | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42205 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Not Started | Will be a new design (short supports) | 0% | 2026-05-14 | 2026-05-23 | Not Started | Not anchored due to concrete joint and future change on the structure MPH13 | 0% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Not started | Belts are not installed | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42405 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42505 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42605 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42705 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42805 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42510 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42610 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-05-14 | 2026-05-23 | Not Started | Waiting M.E | 0% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42710 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-05-14 | 2026-05-23 | Not Started | Waiting M.E | 0% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42810 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-05-14 | 2026-05-23 | Not Started | Waiting M.E | 0% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42855 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-05-14 | 2026-05-23 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42090 | 1 | 2026-05-04 | 2026-05-13 | Complete | DEEP END IDLER CONNECTION BRACKET O PLATE | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42092 | 1 | 2026-05-04 | 2026-05-13 | Complete | DEEP END IDLER CONNECTION BRACKET O PLATE | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42094 | 1 | 2026-05-04 | 2026-05-13 | Complete | DEEP END IDLER CONNECTION BRACKET O PLATE | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42096 | 1 | 2026-05-04 | 2026-05-13 | Complete | DEEP END IDLER CONNECTION BRACKET O PLATE | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-05-24 | 2026-06-02 | Complete | Complete | 100% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42098 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-05-24 | 2026-06-02 | Not Started | At the green-mile , should be on short supports on top of strucure | 0% | 2026-05-24 | 2026-06-02 | Not Started | At the green-mile , should be on short supports on top of strucure | 0% | 2026-06-25 | 2026-07-09 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-20 | 2026-07-29 | Not Started | Complete | 100% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42100 | 1 | 2026-05-04 | 2026-05-13 | Not Started | Missing material delivery | 0% | 2026-05-24 | 2026-06-02 | Not Started | Missing material delivery | 0% | 2026-05-24 | 2026-06-02 | Not Started | Missing material delivery | 0% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42105 | 1 | 2026-05-04 | 2026-05-13 | In Progress | 3-phase to confirm | 50% | 2026-05-24 | 2026-06-02 | Not Started | Missing material delivery | 0% | 2026-05-24 | 2026-06-02 | Not Started | Missing material delivery | 0% | 2026-06-25 | 2026-07-09 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-20 | 2026-07-29 | Not Started | missing material delivery | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42110 | 1 | 2026-05-04 | 2026-05-13 | In Progress | Complete | 100% | 2026-05-24 | 2026-06-02 | Not Started | Complete | 100% | 2026-05-24 | 2026-06-02 | Not Started | Complete | 100% | 2026-07-10 | 2026-07-14 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-30 | 2026-08-08 | Not Started | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42114 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | Complete | 100% | 2026-07-10 | 2026-07-14 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42215 | 1 | 2026-05-04 | 2026-05-13 | In Progress | Not complete due to cut to fit | 25% | 2026-06-02 | 2026-06-11 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-06-02 | 2026-06-11 | Not Started | Not anchored due to concrete joint | 0% | 2026-07-10 | 2026-07-14 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-07-15 | 2026-07-19 | Not started | waiting for upstrem conveyor to install | 0% | 2026-07-30 | 2026-08-08 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42265 | 1 | 2026-05-04 | 2026-05-13 | In Progress | Missing 9'0 SB (Drive has to be intalled in this bed) | 25% | 2026-06-02 | 2026-06-11 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-06-02 | 2026-06-11 | Not Started | Upstrem conveyor | 0% | 2026-07-10 | 2026-07-14 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-07-15 | 2026-07-19 | Not started | waiting for upstrem conveyor to install | 0% | 2026-07-30 | 2026-08-08 | Not Started | waiting for upstrem conveyor to install | 0% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42360 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-06-02 | 2026-06-11 | Not Started | Missing material | 0% | 2026-07-10 | 2026-07-14 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42315 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42365 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42415 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42515 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42615 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-06-02 | 2026-06-11 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42715 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42815 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42860 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-06-12 | 2026-06-21 | Not Started | Missing material | 0% | 2026-07-10 | 2026-07-14 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42865 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-06-12 | 2026-06-21 | Not Started | No straddle supports on site | 0% | 2026-07-10 | 2026-07-14 | Not Started | No Straddle Supports on site | 0% | 2026-07-15 | 2026-07-19 | Not started | No Straddle Supports on site | 0% | 2026-07-30 | 2026-08-08 | Not Started | No Straddle Supports on site | 0% | 2026-08-09 | 2026-08-16 | Complete | NA | 100% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42305 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Complete | 100% | 2026-07-10 | 2026-07-14 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42355 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Complete | 100% | 2026-07-10 | 2026-07-14 | WIP | Waiting for new belt shipment | 50% | 2026-07-15 | 2026-07-19 | Not started | Waiting for new belt shipment | 0% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42210 | 1 | 2026-05-04 | 2026-05-13 | Complete | drive wrong low profile | 100% | 2026-06-12 | 2026-06-21 | Not Started | Missing material delivery | 0% | 2026-06-12 | 2026-06-21 | Not Started | Missing material delivery | 0% | 2026-07-10 | 2026-07-14 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42310 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-06-12 | 2026-06-21 | Not Started | Missing material | 0% | 2026-07-10 | 2026-07-14 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42410 | 1 | 2026-05-04 | 2026-05-13 | Complete | Complete | 100% | 2026-06-12 | 2026-06-21 | Not Started | Waiting for material to be delivered (Hat channles) | 0% | 2026-06-12 | 2026-06-21 | Not Started | Missing material | 0% | 2026-07-10 | 2026-07-14 | Complete | Complete | 100% | 2026-07-15 | 2026-07-19 | Complete | Complete | 100% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
B-24-04663-CP42 | 42260 | 1 | 2026-05-04 | 2026-05-13 | Complete | Drive wrong | 95% | 2026-06-12 | 2026-06-21 | Not Started | Missing material delivery | 0% | 2026-06-12 | 2026-06-21 | Not Started | Missing material delivery | 0% | 2026-07-10 | 2026-07-14 | Not Started | missing material delivery | 0% | 2026-07-15 | 2026-07-19 | Not started | missing material delivery | 0% | 2026-07-30 | 2026-08-08 | Complete | Complete | 100% | 2026-08-09 | 2026-08-16 | Blocked | Missing Material Delivery | 0% | 2026-11-11 | 2026-11-17 | Not Started | 0%
Total |  | 39 |  |  |  |  | 92.18% |  |  |  |  | 38.46% |  |  |  |  | 38.46% |  |  |  |  | 39.74% |  |  |  |  | 25.64% |  |  |  |  | 69.23% |  |  |  |  | 33.33% |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 3.9 | 3.595 | 92.18%
Erected | 30% | 11.7 | 4.5 | 38.46%
Anchored | 10% | 3.9 | 1.5 | 38.46%
Belting | 20% | 7.8 | 3.1 | 39.74%
Bottom Pans | 5% | 1.95 | 0.5 | 25.64%
Side Guide | 20% | 7.8 | 5.4 | 69.23%
Netting | 5% | 1.95 | 0.65 | 33.33%
Total Completion | 100% | 39 | 19.245 | 49.35%
Note on Q4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be a new design (short supports)
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LACKS SUPPORT
Note on Q11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be a new design (short supports)
Note on Q12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be a new design (short supports)
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LACKS SUPPORT
Note on Q13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be a new design (short supports)
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: doesn't have a band
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: doesn't have a band
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: doesn't have a band
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: doesn't have a band
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drive isn't the one that arrived, it's incorrect, there's no information in the ISC
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: upstream conveyor 42210 missing the drive
Note on Q24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: waiting for upstrem conveyor to install
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cut to fit not done due to upstream conveyor 42260 drive missing
Note on Q25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: waiting for upstrem conveyor to install
Note on Q26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing material (sent for powder coat & Hat channles are ordered)
Note on Q34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing material (sent for powder coat & Hat channles are ordered)
Note on G36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRONG BAND
Note on Q39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing material (sent for powder coat & Hat channles are ordered)
Note on Q40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Missing material (sent for powder coat & Hat channles are ordered)

## CP50
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide/Detail - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP50 | 50005 | 1 | 2026-05-28 | 2026-06-02 | Complete | 41027200 | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50010 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50012 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50015 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50020 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50030 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-29 | 2026-07-05 | In progress | Not cooked | 80% | 2026-07-12 | 2026-07-14 | In Progress |  | 80% | 2026-07-15 | 2026-07-21 | In Progress |  | 80% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50035 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50036 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50040 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50045 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50050 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50055 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50105 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50110 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50112 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50115 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 90% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50120 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50130 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-29 | 2026-07-05 | In progress |  | 50% | 2026-07-12 | 2026-07-14 | In Progress |  | 80% | 2026-07-15 | 2026-07-21 | In Progress |  | 80% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50140 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete | banda corta | 60% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50145 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50150 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50155 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 95% | 2026-06-03 | 2026-06-09 | Complete |  | 90% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50205 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-03 | 2026-06-09 | In Progress | Waiting for Platform | 80% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | In Progress |  | 80% | 2026-07-15 | 2026-07-21 | In Progress |  | 80% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50210 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Not Started |  | 50% | 2026-06-03 | 2026-06-09 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Complete |  | 50% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 50% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50215 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 95% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50220 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50225 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50230 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50235 | 1 | 2026-05-28 | 2026-06-02 | Complete | missing carga | 95% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-03 | 2026-06-09 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | falta cocinar | 90% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50240 | 1 | 2026-05-28 | 2026-06-02 | Complete | hss pendiente | 95% | 2026-06-03 | 2026-06-09 | Not Started |  | 100% | 2026-06-03 | 2026-06-09 | Not Started | No road blocks | 0% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50245 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started | No road blocks | 100% | 2026-06-10 | 2026-06-16 | Not Started | No road blocks | 0% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete | No road blocks | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50251 | 1 | 2026-05-28 | 2026-06-02 | Complete | hss pendiente | 95% | 2026-06-10 | 2026-06-16 | Not Started | ubicacion de motor | 95% | 2026-06-10 | 2026-06-16 | Not Started | Waiting for HHS prints | 0% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50255 | 1 | 2026-05-28 | 2026-06-02 | Complete | hss pendiente | 95% | 2026-06-10 | 2026-06-16 | Not Started |  | 100% | 2026-06-10 | 2026-06-16 | Not Started | No road blocks | 0% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50260 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started | No road blocks | 0% | 2026-06-10 | 2026-06-16 | Not Started | No road blocks | 0% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 80% | 2026-07-12 | 2026-07-14 | Complete | Not needed for the line | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 80% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50265 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50270 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50275 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50280 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50285 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50290 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50295 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50300 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50305 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | In Progress |  | 80% | 2026-06-10 | 2026-06-16 | In Progress |  | 80% | 2026-06-29 | 2026-07-05 | Not Started |  | 80% | 2026-07-12 | 2026-07-14 | In Progress |  | 100% | 2026-07-15 | 2026-07-21 | In Progress |  | 80% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50310 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 70% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50315 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 70% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50320 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50325 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50330 | 1 | 2026-05-28 | 2026-06-02 | Complete | 49379603-5575964 | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50405 | 1 | 2026-05-28 | 2026-06-02 | Complete | pendiente hss | 95% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Complete |  | 80% | 2026-07-12 | 2026-07-14 | Not Started | No road blocks | 0% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50415 | 709 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50420 | 649 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started | No road blocks | 0% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
|  | 1 |  |  |  | 84296200
B-24-04663-CP50 | 50435 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 0% | 2026-07-12 | 2026-07-14 | Complete | Not needed for the line | 100% | 2026-07-15 | 2026-07-21 | Not Started |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50440 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete | Not needed for the line | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50445 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Not Started |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
|  | 66 |  |  |  | 41026700
B-24-04663-CP50 | 50450 | 1 | 2026-05-28 | 2026-06-02 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-10 | 2026-06-16 | Complete |  | 100% | 2026-06-29 | 2026-07-05 | Complete |  | 100% | 2026-07-12 | 2026-07-14 | Complete |  | 100% | 2026-07-15 | 2026-07-21 | Complete |  | 100% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50455 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 90% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50460 | 1 | 2026-05-28 | 2026-06-02 | Not Started | 41027200 | 90% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50465 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50505 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-29 | 2026-07-05 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50510 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 100% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-06-10 | 2026-06-16 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-15 | 2026-07-21 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50515 | 1 | 2026-05-28 | 2026-06-02 | Not Started |  | 100% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50701 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50702 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50703 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50704 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50705 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50706 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50707 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50709 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50710 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50711 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50712 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50713 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50714 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50715 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50716 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50717 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50718 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50719 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50720 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50721 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50722 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50723 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50724 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50725 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50726 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50727 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50728 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50729 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50730 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-06-17 | 2026-06-23 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50731 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50732 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50733 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50734 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50735 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50736 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50737 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50738 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50739 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50740 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50741 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50742 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50743 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50744 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50745 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50746 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50747 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50748 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50749 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50750 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50751 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50752 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50753 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50754 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50755 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP50 | 50756 | 1 | 2026-05-28 | 2026-06-02 | Not Started | MDR Workstations | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-06-24 | 2026-06-28 | Not Started |  | 0% | 2026-07-06 | 2026-07-11 | Not Started |  | 0% | 2026-07-12 | 2026-07-14 | Not Started |  | 0% | 2026-07-22 | 2026-07-27 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
Total |  | 116 |  |  |  |  | 36% |  |  |  |  | 28% |  |  |  |  | 28% |  |  |  |  | 21% |  |  |  |  | 17% |  |  |  |  | 33% |  |  |  |  | 0% |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 11.6 | 5.745 | 49.53%
Erected | 30% | 34.8 | 11.58 | 33.28%
Anchored | 10% | 11.6 | 3.41 | 29.4%
Belting | 20% | 23.2 | 4.94 | 21.29%
Bottom Pans | 5% | 5.8 | 1.07 | 18.45%
Side Guide | 20% | 23.2 | 1.8425 | 7.942%
Netting | 5% | 5.8 | 0 | 0%
Total Completion | 100% | 116 | 28.5875 | 24.64%
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR-710.MRG.BLNSE.EXT.30D.6.5.RIVER GRAY
Note on G54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT STD NEEDLED FELT 21"W
Note on G58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT STD NEEDLED FELT 20"W
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W

## CP51
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide/Detail - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP51 | 04663_51005 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41022800-11180652 | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
41044300
B-24-04663-CP51 | 04663_51015 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Not Started |  | 20% | 2026-08-01 | 2026-08-03 | In Progress |  | 100% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51020 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41027200 | 50% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-07-19 | 2026-07-24 | Complete |  | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51025 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-07-19 | 2026-07-24 | Complete |  | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51028 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41027200 | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-07-19 | 2026-07-24 | Complete |  | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked | NA | 100% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51030 | 1 | 2026-06-17 | 2026-06-22 | Complete | 47010500-9305734 | 90% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51035 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | In Progress | In Progress | 50% | 2026-08-01 | 2026-08-03 | In Progress |  | 50% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked | NA | 100% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51040 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 90% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 50% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51045 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49042700 | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51050 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 492534430-11175596 | 50% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51055 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51060 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51065 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51105 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51115 | 1 | 2026-06-17 | 2026-06-22 | Complete | 40099300-11180602 | 90% | 2026-06-23 | 2026-06-29 | Complete | Complete | 80% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 100% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
40036200-11175547
B-24-04663-CP51 | 04663_51120 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41044300 | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51125 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51128 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51130 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51135 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51140 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 90% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51145 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51150 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49253230-11180618 | 50% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49383930-11175578
49253430-11175584
B-24-04663-CP51 | 04663_51155 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51160 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51165 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51205 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41044300 | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51215 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 90% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 80% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 80% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51220 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 100% | 2026-07-19 | 2026-07-24 | Complete |  | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
41044300
B-24-04663-CP51 | 04663_51225 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Complete | Complete | 100% | 2026-08-01 | 2026-08-03 | Not Started | Not Started | 0% | 2026-08-04 | 2026-08-10 | Not Started | Not Started | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51228 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41027200 | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Complete | 100% | 2026-07-19 | 2026-07-24 | Complete | Complete | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51230 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 50% | 2026-07-19 | 2026-07-24 | Complete | Complete | 100% | 2026-08-01 | 2026-08-03 | Not Started | Not Started | 0% | 2026-08-04 | 2026-08-10 | Not Started | Not Started | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51235 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 80% | 2026-07-19 | 2026-07-24 | In Progress | In Progress | 80% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51240 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 80% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 80% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51245 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51250 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49253230-11180618 | 50% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49383930-11175578
49253430-11175584
B-24-04663-CP51 | 04663_51255 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51260 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51265 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51305 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41044300 | 50% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51308 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51310 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51312 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-06-23 | 2026-06-29 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51315 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 90% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 80% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 80% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51320 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41044300 | 50% | 2026-06-23 | 2026-06-29 | Complete |  | 0% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
41169100-11025567
B-24-04663-CP51 | 04663_51325 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51330 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51335 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | In Progress | In Progress | 80% | 2026-07-19 | 2026-07-24 | In Progress | In Progress | 80% | 2026-08-01 | 2026-08-03 | In Progress |  | 0% | 2026-08-04 | 2026-08-10 | In Progress |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51340 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51345 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49175200-11417087 | 100% | 2026-06-23 | 2026-06-29 | Complete | Complete | 100% | 2026-06-23 | 2026-06-29 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51350 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49253230-11180618 | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49383930-11175578 x 2
49253430-11175584
B-24-04663-CP51 | 04663_51355 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51360 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51365 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51405 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41044300 | 50% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51408 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51410 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 49182200-11180682 | 50% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51412 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51414 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41027200 | 50% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51415 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 75% | 2026-06-30 | 2026-07-05 | In Progress | In Progress | 90% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 90% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51420 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | faltan soportes | 50% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51425 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 100% | 2026-07-19 | 2026-07-24 | Complete | Complete | 100% | 2026-08-01 | 2026-08-03 | Not Started | Not Started | 0% | 2026-08-04 | 2026-08-10 | Not Started | Not Started | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51430 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 100% | 2026-07-19 | 2026-07-24 | Complete | Complete | 100% | 2026-08-01 | 2026-08-03 | Not Started | Not Started | 0% | 2026-08-04 | 2026-08-10 | Not Started | Not Started | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51431 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51432 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49175500-11548771 | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51435 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 90% | 2026-06-30 | 2026-07-05 | In Progress | In Progress | 90% | 2026-07-19 | 2026-07-24 | In Progress | In Progress | 90% | 2026-08-01 | 2026-08-03 | In Progress |  | 90% | 2026-08-04 | 2026-08-10 | In Progress |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51440 | 1 | 2026-06-17 | 2026-06-22 | Complete | 40036200-11196914 | 95% | 2026-06-30 | 2026-07-05 | Complete | Complete | 90% | 2026-06-30 | 2026-07-05 | In Progress | In Progress | 90% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | In Progress |  | 80% | 2026-08-04 | 2026-08-10 | Not Started |  | 90% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51445 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49182200-11180686 | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49182200-11180684
B-24-04663-CP51 | 04663_51450 | 1 | 2026-06-17 | 2026-06-22 | Complete | 49253230-11175582 | 70% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started | Not Started | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49253430-11175596
B-24-04663-CP51 | 04663_51455 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51460 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51465 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51555 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started |  | 100% | 2026-07-19 | 2026-07-24 | Not Started |  | 80% | 2026-08-01 | 2026-08-03 | Not Started | Installed but not leveled or centered | 0% | 2026-08-04 | 2026-08-10 | Not Started | Installed but not leveled or centered | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51560 | 1 | 2026-06-17 | 2026-06-22 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Complete | Complete | 100% | 2026-06-30 | 2026-07-05 | Not Started | Not anchored | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 100% | 2026-08-01 | 2026-08-03 | Not Started |  | 100% | 2026-08-04 | 2026-08-10 | Not Started | Installed but not leveled or centered | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51565 | 1 | 2026-06-17 | 2026-06-22 | Complete | pendiente hss | 100% | 2026-06-30 | 2026-07-05 | Not Started | MISSING DRIVE | 90% | 2026-06-30 | 2026-07-05 | Not Started | Installed but not leveled or centered | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started | Installed but not leveled or centered | 0% | 2026-08-04 | 2026-08-10 | Not Started | Installed but not leveled or centered | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
| 04663_51570 | 1 | 2026-06-17 | 2026-06-22 | Complete |  | 100% | 2026-06-30 | 2026-07-05 | Not Started |  | 100% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started | Installed but not leveled or centered | 0% | 2026-08-04 | 2026-08-10 | Not Started | Installed but not leveled or centered | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51575 | 1 | 2026-06-17 | 2026-06-22 | Complete | 41027200 | 95% | 2026-06-30 | 2026-07-05 | Complete |  | 100% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51580 | 1 | 2026-06-17 | 2026-06-22 | Complete |  | 100% | 2026-06-30 | 2026-07-05 | Complete |  | 100% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51585 | 1 | 2026-06-17 | 2026-06-22 | Not Started | falta una cama de 12' | 95% | 2026-06-30 | 2026-07-05 | Not Started |  | 80% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51590 | 1 | 2026-06-17 | 2026-06-22 | Not Started | motor danado | 80% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51595 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51600 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 41044300 | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
41036100
B-24-04663-CP51 | 04663_51605 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51610 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 49182200-11180682 | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49182200-11180680 x2
B-24-04663-CP51 | 04663_51650 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51655 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 49321700-11175574 x2 | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51660 | 1 | 2026-06-17 | 2026-06-22 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51665 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 49117101-11175588 | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51701 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51702 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51703 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51704 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51705 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51706 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51707 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51708 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51709 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-07-28 | 2026-07-30 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51710 | 1 | 2026-06-17 | 2026-06-22 | Not Started | 49182200-11180682 X2 | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
49182200-11180680 X2
B-24-04663-CP51 | 04663_51711 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51712 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-06-30 | 2026-07-05 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51713 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-19 | 2026-07-24 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-04 | 2026-08-10 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51714 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51715 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51716 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51717 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51718 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51719 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51720 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51721 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51722 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51723 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51724 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51725 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51726 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51727 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51728 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51730 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP51 | 04663_51731 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51732 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51733 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51734 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51735 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51736 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51737 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51738 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51739 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51740 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51741 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51742 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51743 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51744 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51745 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51746 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51747 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51748 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51749 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51750 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51751 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51752 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51753 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51754 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51755 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51756 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51757 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51758 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51759 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51760 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51761 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51763 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51764 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-06 | 2026-07-12 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51765 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51766 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51767 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51768 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51769 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51770 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51771 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51772 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51773 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51774 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51775 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51776 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51777 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51778 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51779 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51780 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51781 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51782 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51783 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51784 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51785 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51786 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51787 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51788 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51789 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51790 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51791 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51792 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51793 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51794 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51795 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51796 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51797 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51798 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51799 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51800 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51801 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51802 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51803 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51804 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51805 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51806 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51807 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51808 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51809 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51810 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51811 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51812 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
B-24-04663-CP51 | 04663_51813 | 1 | 2026-06-17 | 2026-06-22 | Not Started | MDR Workstations | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-13 | 2026-07-18 | Not Started |  | 0% | 2026-07-25 | 2026-07-31 | Not Started |  | 0% | 2026-08-01 | 2026-08-03 | Not Started |  | 0% | 2026-08-11 | 2026-08-16 | Not Started |  | 0% | 2026-08-17 | 2026-08-20 | Blocked |  | 0% |  |  | Not Started | 0%
Total |  | 199 |  |  |  |  | 22% |  |  |  |  | 24.8% |  |  |  |  | 9% |  |  |  |  | 6% |  |  |  |  | 5% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete %
Prep | 10% | 19.9 | 5.265 | 26.46%
Erected | 30% | 59.7 | 14.805 | 24.8%
Anchored | 10% | 19.9 | 2.05 | 10.3%
Belting | 20% | 39.8 | 2.8 | 7.035%
Bottom Pans | 5% | 9.95 | 0.45 | 4.523%
Side Guide | 20% | 39.8 | 1.62 | 4.07%
Netting | 5% | 9.95 | 0.1 | 1.005%
Total Completion | 100% | 199 | 27.09 | 13.61%
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .200 BELT CENTERDRIVE.22BF.RH PU.URETH PULLEY.ENCODER ROLLER.BAL-3HP-460V-PREM.DGE-26-A-10-R-180.DVR-P36-8M-50-1610.DVN-P56-8M-50-2517.GB-HT200-1224-8M-50.RIVER GRAY
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .200 BELT CENTERDRIVE.22BF.RH PU.URETH PULLEY.ENCODER ROLLER.BAL-3HP-460V-PREM.DGE-26-A-10-R-180.DVR-P36-8M-50-1610.DVN-P56-8M-50-2517.GB-HT200-1224-8M-50.RIVER GRAY
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB CRV 60D ASSY TT 2"C.22"BF.TG254AB.9.75"HT.RIVER GRAY
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MDR 710 FRAME GROUNDING FLAT
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC UPR TRNS.22"BF.30"ZN, 2ZN.LH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496655.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IQ DIRECT CTR DRV ASSY.22"BF.12-0.RH.DIRECT DRIVE.STANDARD.2"CTRS.3 FT ZN OUTSIDE OPP SIDE.G196AB-BK.BAL-3HP-460V-PREM.DGE-35-A-25-H-180.DODGE A35.RIVER GRAY
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IS ASSY.12-0.22"BF.RH.STANDARD.2"CTRS.3 FT ZN OUTSIDE OPP SIDE.G196AB-BK.RIVER GRAY
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC UPR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496655.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .200 BELT INTERMEDIATE SB.3'LG.22"BF.CHAN-CHAN.RIVER GRAY
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR FWB STRT INC ASSY.22"BF.30"ZN.RH WIRE.RLR LOW.120"OAL.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-492186.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC UPR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496655.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 41044300
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .200 BELT INTERMEDIATE SB.12'LG.22"BF.CHAN-CHAN.RIVER GRAY
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-PWDR INCR.22"BF.2"CTRS.RH WIRE.LH OBLT.RLR LOW.1-8.G196AB MDR DGR.STD TORQ DGR HON STSS.180FPM INT.HON2018.WH-491908.RIVER GRAY
Note on G62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.RH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.RH CURVE LH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-INCR.22"BF.2"CTRS.RH WIRE.LH OBLT.RLR LOW.3"OAL.G196AB MDR DGR.RMT CNTL.BNR X2X.WH-491908.RIVER GRAY
Note on G80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .611 IS ASSY.12-0.22"BF.RH.AIR TRANS.3"CTRS.G196AB-BK.RIVER GRAY
Note on G81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.LH CURVE RH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.RH CURVE LH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC LWR TRNS.22"BF.30"ZN, 2ZN.LH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496654.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR NGFWB CART INC UPR TRNS.22"BF.30"ZN, 2ZN.LH WIRE.RLR LOW.120FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-496655.PREM HORZ BELT DGR HON HTSS.PREM INC BELT DGR HON HTSS.RIVER GRAY
Note on G92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT 2PL LR MONOFILAMENT 20"W
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .810 VB END IDL ASSY.22"BF.LH BELT.G196AB.RIVER GRAY
Note on G97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT HABASIT MAT TOP 4137 20"W
Note on G98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 BT LR NEEDLED FELT BACK 20"W
Note on G100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.RH CURVE LH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.LH CURVE RH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.LH CURVE RH WIRE.22"BF.30"ZN.60D.48"IR.RLR LOW.TR 197 48.0"IR DGR AX7.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.WH-491083.RIVER GRAY
Note on G105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710 JCT 30D LM.22"BF.3"CTRS.NON-CVR JCT HON STSS.RLR LOW.50LB WHL.180FPM INT.HON2018.RMT CNTL.BNR X2X.WH-490027.RIVER GRAY
Note on G115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.RH CURVE LH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY
Note on G116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .MDR 710-CRV.LH CURVE RH WIRE.22"BF.CC.30"ZN.60D.48"IR.RLR LOW.STD TORQ DGR HON STSS.180FPM INT.PE SICK ZLD18 PNP RETRO 4PIN.HON2018.RMT CNTL.BNR X2X.WH-491910.RIVER GRAY

## CP52
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide/Detail - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
|  |  | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP52 | 52560 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52585 | 1 | 2026-06-22 | 2026-06-27 | Not Started |  | 100% | 2026-06-28 | 2026-07-06 | Not Started |  | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52600 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started (Platform Conveyors) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52610 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started (Platform Conveyors) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52010 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52015 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52040 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Complete | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52060 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52065 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52090 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52110 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52115 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52140 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52165 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52190 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52215 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52240 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52265 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52290 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52315 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52340 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52365 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52390 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52415 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52440 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52465 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52490 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52515 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52540 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52555 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52570 | 1 | 2026-06-22 | 2026-06-27 | Not Started | falta carga | 95% | 2026-06-28 | 2026-07-06 | Not Started |  | 70% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52580 | 1 | 2026-06-22 | 2026-06-27 | Not Started |  | 100% | 2026-06-28 | 2026-07-06 | Not Started |  | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52590 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started (long straddle supports) | 100% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 90% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52615 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started (Platform Conveyors) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52035 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52042 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52044 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52046 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52048 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52049 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52050 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52085 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52092 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52094 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52096 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52098 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52099 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52100 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52135 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | In progress | 90% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52142 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52144 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52146 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52148 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52149 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52150 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52185 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52192 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52194 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52196 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52198 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52199 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52200 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52235 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52242 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52244 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52246 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52248 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52249 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52250 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52285 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52292 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52294 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52296 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52298 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52299 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52300 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52335 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52342 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52344 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52346 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52348 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52349 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52350 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52385 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52392 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52394 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52396 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52398 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52399 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52400 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52435 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52442 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52444 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52446 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52448 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52449 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52450 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52485 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52492 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52494 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52496 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52498 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52499 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52500 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52535 | 1 | 2026-06-22 | 2026-06-27 | Complete | Complete | 100% | 2026-06-28 | 2026-07-06 | In Progress | In Progress | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 50% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 90% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52542 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52544 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52546 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52548 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52549 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52550 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52660 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52665 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52670 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-06-28 | 2026-07-06 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52701 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52702 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52703 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP52 | 52704 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52705 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52706 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52707 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52708 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52709 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52710 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52711 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52712 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52713 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-06-28 | 2026-07-06 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52714 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52715 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52716 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52717 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52718 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52719 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52720 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52721 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52722 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52723 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52724 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52725 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52726 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52727 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52728 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52729 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52730 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52731 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52732 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52733 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52734 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52735 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52736 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52737 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52738 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52739 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52740 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52741 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52742 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52743 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52744 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52745 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52746 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52747 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52748 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52749 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52750 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52751 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52752 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52753 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52754 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52755 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52756 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52757 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52758 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52759 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52760 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52761 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52762 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52763 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52764 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52765 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52766 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52767 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52768 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52769 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52770 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52771 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52772 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52773 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52774 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52775 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52776 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52777 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52778 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52779 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52780 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52781 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52782 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52783 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52784 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-29 | 2026-08-04 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-16 | 2026-08-23 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  | Not Started | 0%
B-24-04663-CP52 | 52785 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% | 0% | 0% | 0% | 0%
B-24-04663-CP52 | 52786 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0% |  |  |  | 0%
B-24-04663-CP52 | 52787 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52788 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52789 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52790 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52791 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52792 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52793 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52794 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52795 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52796 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52797 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52798 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52799 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52800 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52801 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52802 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52803 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52804 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52805 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52806 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52807 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52808 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52809 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52810 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52811 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52812 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52813 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52814 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52815 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52817 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52818 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52819 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52820 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52821 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52822 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52823 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52824 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52825 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52826 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52827 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52828 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52829 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52830 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52831 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52832 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52833 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52834 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52835 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52836 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52837 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52838 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52839 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52840 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52841 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52842 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52843 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52844 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52845 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52846 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52847 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-07 | 2026-07-15 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52848 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52849 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52850 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52851 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52852 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52853 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52854 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52855 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52856 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52857 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52858 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52859 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52860 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52861 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52862 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52863 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52864 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52865 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52866 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52867 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52868 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52869 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52870 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52871 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52872 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52873 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52874 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52875 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52876 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52877 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52878 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52879 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52880 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52881 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52882 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52883 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52884 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52885 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52886 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52887 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52888 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52889 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52890 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52891 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52892 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52893 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52894 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52895 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52896 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52897 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52898 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52899 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52900 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52901 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52902 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52903 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52904 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52905 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52906 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52907 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52908 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52909 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52910 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52911 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52912 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52913 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52914 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52915 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52916 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52917 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52918 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52919 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52920 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52921 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52922 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52923 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52924 | 1 | 2026-06-22 | 2026-06-27 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-07-16 | 2026-07-28 | Not Started | MDR Work-stations (SOPER'd) | 0% | 2026-08-05 | 2026-08-12 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-13 | 2026-08-15 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-08-24 | 2026-08-31 | Not Started | NA- MDR Work-stations (SOPER'd) | 0% | 2026-09-01 | 2026-09-04 | Blocked | NA- MDR Work-stations (SOPER'd) | 0%
B-24-04663-CP52 | 52005 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52020 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52055 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52070 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52105 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52120 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52155 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52170 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52205 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52220 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52255 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52270 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52305 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52320 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52355 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52370 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52405 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52420 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52455 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52470 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52505 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52520 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52008 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52012 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52025 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52030 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 9%
B-24-04663-CP52 | 52058 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52062 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52075 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 100% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52080 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 100% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Complete | 100%
B-24-04663-CP52 | 52108 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 90% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52112 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52125 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52130 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52158 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52160 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Area Beyond Grid 8 - Not available for install | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52175 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52180 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52225 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52230 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 90% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52275 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52280 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52325 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52330 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52375 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52380 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52425 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52430 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52475 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52480 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52525 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52530 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52558 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52575 | 1 | 2026-06-22 | 2026-06-27 | Not Started | complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Complete | 100% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started |  | 20% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52595 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started (long straddle supports) | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52605 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-08-05 | 2026-08-12 | Not Started | Platform not installed | 0% | 2026-08-13 | 2026-08-15 | Not Started | Platform not installed | 0% | 2026-08-24 | 2026-08-31 | Not Started | Platform not installed | 0% | 2026-09-01 | 2026-09-04 | Blocked | Platform not installed | 0%
B-24-04663-CP52 | 52620 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-08-05 | 2026-08-12 | Not Started | Platform not installed | 0% | 2026-08-13 | 2026-08-15 | Not Started | Platform not installed | 0% | 2026-08-24 | 2026-08-31 | Not Started | Platform not installed | 0% | 2026-09-01 | 2026-09-04 | Blocked | Platform not installed | 0%
B-24-04663-CP52 | 52625 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-08-05 | 2026-08-12 | Not Started | Platform not installed | 0% | 2026-08-13 | 2026-08-15 | Not Started | Platform not installed | 0% | 2026-08-24 | 2026-08-31 | Not Started | Platform not installed | 0% | 2026-09-01 | 2026-09-04 | Blocked | Platform not installed | 0%
B-24-04663-CP52 | 52630 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-07-16 | 2026-07-28 | Not Started | Platform not installed | 0% | 2026-08-05 | 2026-08-12 | Not Started | Platform not installed | 0% | 2026-08-13 | 2026-08-15 | Not Started | Platform not installed | 0% | 2026-08-24 | 2026-08-31 | Not Started | Platform not installed | 0% | 2026-09-01 | 2026-09-04 | Blocked | Platform not installed | 0%
B-24-04663-CP52 | 52655 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
B-24-04663-CP52 | 52565 | 1 | 2026-06-22 | 2026-06-27 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-08-05 | 2026-08-12 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-24 | 2026-08-31 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0%
Total |  | 398 |  |  |  |  | 16.57% |  |  |  |  | 15.35% |  |  |  |  | 4.146% |  |  |  |  | 3.04% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 2.309%
Summary
Task | Weight | Weighted Totals | Complete | Complete % | [32 empty] | x
Prep | 10% | 39.8 | 2.9166 | 7.328%
Erected | 30% | 119.4 | 8.3861 | 7.023%
Anchored | 10% | 39.8 | 0.0041457 | 0.01042%
Belting | 20% | 79.6 | 0.44608 | 0.5604%
Bottom Pans | 5% | 19.9 | 0 | 0%
Side Guide | 20% | 79.6 | 0 | 0%
Netting | 5% | 19.9 | 0.055655 | 0.2797%
Total Completion | 100% | 398 | 11.8085 | 2.967%

## CP-09
CP | Asset | Length | Prep -10% |  |  |  |  | Erected 30% |  |  |  |  | Anchored 10% |  |  |  |  | Belting - 20% |  |  |  |  | Bottom Pans - 5% |  |  |  |  | Side Guide/Detail - 20% |  |  |  |  | Netting Bracket - 5% |  |  |  |  | Run-in
[5 empty] | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | Notes | % Complete | Start | Finish | Status | % Complete
B-24-04663-CP09 | 9005 | 1 |  |  | Not Started | Not Started | 0% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9010 | 1 |  |  | Not Started | Not Started | 0% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9015 | 1 |  |  | Not Started | Not Started | 0% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9018 | 1 |  |  | Not Started | Not Started | 0% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started (Platform Conveyors) | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9020 | 1 |  |  | Not Started | Not Started | 0% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9025 | 1 |  |  | Complete | Not Started | 0% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9030 | 1 |  |  | Complete | Not Started | 0% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9035 | 1 |  |  | Not Started | Not Started | 100% |  |  | Not Started | Not Started | 80% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9040 | 1 |  |  | Complete | Not Started | 0% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9045 | 1 |  |  | Complete | Not Started | 0% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9815 | 1 |  |  | Not Started | Not Started | 100% |  |  | Not Started | Not Started | 0% | 2026-07-16 | 2026-07-28 | Not Started | Not Started | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9825 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9915 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9925 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9935 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 90% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9945 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9955 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9965 | 1 |  |  | Complete | Not Started | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9975 | 1 |  |  | Complete | Complete | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9985 | 1 |  |  | Complete | Complete | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9992 | 1 |  |  | Complete | Not Started | 0% |  |  | In Progress | Not Started | 0% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 0% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
B-24-04663-CP09 | 9995 | 1 |  |  | Complete | Complete | 100% |  |  | In Progress | Area Beyond Grid 8 - Not available for install | 80% | 2026-07-16 | 2026-07-28 | In Progress | WIP- (Anchored Diagonally) | 80% | 2026-07-29 | 2026-08-04 | Not Started | Not Started | 0% | 2026-08-13 | 2026-08-15 | Not Started | Not Started | 0% | 2026-08-16 | 2026-08-23 | Not Started | Not Started | 0% | 2026-09-01 | 2026-09-04 | Blocked | Not Started | 0% | 2026-11-06 | 2026-11-12 | Not Started | 0%
Total |  | 22 |  |  |  |  | 54.55% |  |  |  |  | 36.82% |  |  |  |  | 32.73% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0%
Summary
Task | Weight | Weighted Totals | Complete | Complete % | [32 empty] | x
Prep | 1% | 0.22 | 0.054545 | 24.79%
Erected | 1% | 0.22 | 0.11045 | 50.21%
Anchored | 1% | 0.22 | 0.032727 | 14.88%
Belting | 1% | 0.22 | 0 | 0%
Bottom Pans | 1% | 0.22 | 0 | 0%
Side Guide | 1% | 0.22 | 0 | 0%
Netting | 1% | 0.22 | 0 | 0%
Total Completion | 7% | 1.54 | 0.19773 | 12.84%

## CP09
Project_Number_CP | Product Name | Asset_Number | Length | Anchored and leveled? | Belting installed? | Bottom Pans installed? | Netting Bracket installed | Side guide installed? | Run-in complete?
B-24-04663-CP09 | 460 | 9005 | 1
B-24-04663-CP09 | 460 | 9010 | 1
B-24-04663-CP09 | 460 | 9015 | 1
B-24-04663-CP09 | 460 | 9018 | 1
B-24-04663-CP09 | 460 | 9020 | 1
B-24-04663-CP09 | 460 | 9025 | 1
B-24-04663-CP09 | 460 | 9030 | 1
B-24-04663-CP09 | 460 | 9035 | 1
B-24-04663-CP09 | 460 | 9040 | 1
B-24-04663-CP09 | 460 | 9045 | 1
B-24-04663-CP09 | 460 | 9815 | 1
B-24-04663-CP09 | 460 | 9825 | 1
B-24-04663-CP09 | 460 | 9915 | 1
B-24-04663-CP09 | 460 | 9925 | 1
B-24-04663-CP09 | 460 | 9935 | 1
B-24-04663-CP09 | 460 | 9945 | 1
B-24-04663-CP09 | 460 | 9955 | 1
B-24-04663-CP09 | 460 | 9965 | 1
B-24-04663-CP09 | 460 | 9975 | 1
B-24-04663-CP09 | 460 | 9985 | 1
B-24-04663-CP09 | 460 | 9995 | 1
B-24-04663-CP09 | ECC | 09005 | 1
B-24-04663-CP09 | ECC | 09010 | 1
B-24-04663-CP09 | ECC | 09015 | 1
B-24-04663-CP09 | ECC | 09018 | 1
B-24-04663-CP09 | ECC | 09020 | 1
B-24-04663-CP09 | ECC | 09025 | 1
B-24-04663-CP09 | ECC | 09030 | 1
B-24-04663-CP09 | ECC | 09035 | 1
B-24-04663-CP09 | ECC | 09040 | 1
B-24-04663-CP09 | ECC | 09045 | 1
B-24-04663-CP09 | ECC | 09815 | 1
B-24-04663-CP09 | ECC | 09825 | 1
B-24-04663-CP09 | ECC | 09915 | 1
B-24-04663-CP09 | ECC | 09925 | 1
B-24-04663-CP09 | ECC | 09935 | 1
B-24-04663-CP09 | ECC | 09945 | 1
B-24-04663-CP09 | ECC | 09955 | 1
B-24-04663-CP09 | ECC | 09965 | 1
B-24-04663-CP09 | ECC | 09975 | 1
B-24-04663-CP09 | ECC | 09985 | 1
B-24-04663-CP09 | ECC | 09995 | 1
Total |  |  | 1
43
Applied filters: Included (1) B-24-04663 (Project_Number) + CP09 (CP)